## Slide 1: calib2 passed. Round 1 starts now.
A3 · SECOND CALIBRATION · ROUND 1
What the second calibration showed, what to watch in the A3 batches, and how the waves and the reserve are released from here.
Groups 14 and 15 · extended team · 18 October 2026
Notes: Purpose: close the second calibration with its results, turn them into a few working recommendations, and explain how round 1 is released in waves, including when the reserve is used. The last slide lists the next steps and the decisions still open.

## Slide 2: Every cross-group pair cleared the gate
CALIB2 · IN THREE NUMBERS
16 / 16
cross-group pairs at Cohen’s κ ≥ 0.6
Lowest pair 0.71, mean 0.87
0.87
Fleiss’ κ, all 8 annotators, 27 items
calib30 was 0.47, in a different setup
1.7 min
per package, median of those who logged time
Range 1.1–2.8 min, 5 of 8 logged
Decision: A3 round 1 is open. Wave 1 is already in your folders.
calib2 and A3 round 1 · 2 · calib2_report.md, 8 of 8 complete
Notes: The gate in the contract is Cohen’s kappa of at least 0.6 for every pair of annotators from different groups: 16 pairs. All 16 pass; the lowest is 0.71 and the mean 0.87. Fleiss’ kappa over the 8 annotators is 0.87. The calib30 figure of 0.47 came from a group session with an earlier version of the rules, so the two numbers are not directly comparable; the next slides explain why calib2 agreement is high. Time: five people logged minutes, between 30 and 76 for 27 items.

## Slide 3: Cohen’s κ for every G14–G15 pair
AGREEMENT · THE GATE
κ | G15-01 | G15-02 | G15-03 | G15-04
G14-01 | 0.96 | 0.75 | 0.92 | 1.00
G14-02 | 0.92 | 0.79 | 0.92 | 0.96
G14-03 | 0.88 | 0.71 | 0.83 | 0.92
G14-04 | 0.88 | 0.83 | 0.87 | 0.83
Target 0.6 · every cell passes · same-group pairs 0.75–0.96
Three calibrations
eval60 · Cohen 0.63 between the two groups
calib30 · Fleiss 0.47; 3 of 21 pairs at 0.6
calib2 · Fleiss 0.87; 16 of 16 cross pairs
calib2 is the first with guide rev3.1, individual work and the pre-label shown, as in A3.
calib2 and A3 round 1 · 3 · κ on the primary label, 27 items · contract §7, §9
Notes: Rows are group 14, columns group 15. These 16 cross-group pairs are the ones the contract counts, because every A3 package is annotated by one person from each group. The lowest column is the annotator who corrected the pre-label most often; lower agreement there reflects independent reading, not a problem. The three calibrations used different setups, so the trend is encouraging but not a like-for-like comparison: eval60 was blind, calib30 a group session, calib2 individual with the pre-label visible, exactly as A3 runs.

## Slide 4: 16 of 216 answers changed the pre-label
CORRECTION RATE · READ IT WITH Κ
Everyone saw the same pre-label on high-confidence items, so part of the agreement is shared confirmation. Per person the rate ranged from 0% to 22%.
Background
5 of 24 · 21%
Basis
5 of 24 · 21%
Comparison
3 of 24 · 12%
Application
1 of 24 · 4%
Improvement/Modification
1 of 24 · 4%
Evidence
1 of 24 · 4%
Gap
0 of 24 · 0%
Identification of the Originator
0 of 24 · 0%
Further Reading
0 of 24 · 0%
calib2 and A3 round 1 · 4 · answers = 8 annotators × 3 items per pre-label · orange: over 10%
Notes: Each pre-label had 3 items, so 24 answers. Background and Basis were corrected most, Comparison next; the other six were corrected at most once. The contract asks us to report kappa together with the correction rate, because both annotators see the same pre-label: a rate near zero in a category would mean confirmation rather than review. Two annotators corrected nothing in calib2; that is not wrong on 27 high-confidence items, but in A3 the rate is what tells us the review is real. The same rate, per set and category, decides the reserve release in round 1.

## Slide 5: Three items, three known boundaries
DEBRIEF · WHERE WE SPLIT
On 24 of 27 items at least 7 of 8 annotators agreed. These three hold 11 of the 16 corrections on slide 4: the orange bars come from them.
K04
Background 4 · Evidence 4
Rule 10: does the citation back a claim, choice or result of the citing authors (Evidence), or describe prior work (Background)?
K23
Basis 4 · Improvement/ Modification 3 · Application 1
Rules 3 and 5: does the current work build on it (Basis), adapt it (I/M) or use it unchanged (Application)?
K13
Comparison 5 · Background 2 · Application 1
Rule 4: does the text compare works with each other, or only list them under a shared topic?
calib2 and A3 round 1 · 5 · per-item spread from calib2_report.md · rules as in guide rev3.1 §6
Notes: These are the only three items without a clear majority of 7 or 8, and they hold 11 of the 16 corrections: K04 gives Background 4 of its 5, K23 gives Basis 4 of its 5, and K13 all 3 of Comparison’s. The majority still matched the pre-label on all 27 items. All three fall on boundaries the guide already names. K04 split evenly between Background and Evidence: rule 10 asks what the citation supports. K23 spread across Basis, Improvement/Modification and Application: rules 3 and 5, build on versus adapt versus use. K13 drew two Background answers against five Comparison: rule 4, comparing versus grouping. Worth reopening these three items together in the debrief, with the rule text open. No item text appears on this slide, because the packages contain unarXive text that stays in the private Sheets.

## Slide 6: Round 1 is about 28 hours per person
TIME · THE WORKLOAD
Each person annotates 990 packages in round 1: 18 batches of 55.
Pace per package | Hours for 990
1.1 min · fastest | 18 h
1.7 min · median | 28 h
2.8 min · slowest | 46 h
The contract planned about 1 minute per package. calib2 included learning the new Sheet, so the pace may improve.
3 of 8 logged no minutes
The Resumen tab of every batch has a cell for total minutes. Fill it in each batch: it is how we plan wave 2 dates and report the workload.
calib2 and A3 round 1 · 6 · minutes for 27 items from 5 annotators: 30, 32, 45, 59, 76
Notes: Five people logged their time for the 27 items: 30, 32, 45, 59 and 76 minutes, which is 1.1 to 2.8 minutes per package, median 1.7. Round 1 gives everyone 18 batches of 55, 990 packages, before any reserve: about 28 hours at the median pace, between 18 and 46 hours across the range. The contract assumed about a minute per package. calib2 was also the first time on the new Sheet layout, so A3 may well go faster; the minutes per batch will tell. Released reserve, if any, adds a little on top.

## Slide 7: Four habits from calib2
RECOMMENDATIONS · FOR EVERY BATCH
1
Read before you confirm
Usually right, not always. Background and Basis were corrected most.
2
Watch the three boundaries
Background vs Evidence (rule 10) · Basis vs Improvement/Modification vs Application (rules 3, 5) · Comparison vs Background (rule 4)
3
Fill every field
Confianza on every row · a note with the rule when you correct · minutes on Resumen
4
Work alone until annotation closes
Don’t discuss packages: each one needs two independent answers.
calib2 and A3 round 1 · 7 · guide rev3.1 and the instructions Sheet in the shared folder
Notes: One: the pre-label comes from at least two of three judges agreeing, so it is right most of the time, but the correction rate is how we show the review is real; Background and Basis were the most corrected in calib2. Two: the three disagreement items map to rules 10, 3 and 5, and 4; keep the instructions Sheet open next to the batch. Three: confidence was missing on some calib2 rows and three people logged no minutes; both feed the report. Four: the second annotation of every package must be independent of the first, so packages are not discussed until annotation closes; questions about the rules are fine, examples from your batch are not.

## Slide 8: Two test sets, six categories, 72 batches
ROUND 1 · WHAT WAS SAMPLED
6
categories with enough supply
2
test sets: T_A owned by G14, T_B owned by G15
3,960
active packages: 330 per set and category
72
batches of 55, every category in every batch
Per person
18 batches, 990 packages: 9 batches from your group’s set (validation) and 9 from the other set (second annotation). Every G14–G15 pair shares 4 or 5 batches.
Per set and category
360 drawn: 330 active, 30 reserve. At most 2 per citing paper and 1 per citation group. All 12 drawn in full; Originator was tightest, 658 and 711 candidates.
calib2 and A3 round 1 · 8 · seed LCR-G14G15-A3-2026 · halves by citing paper · contract §6, §7
Notes: Round 1 covers the six categories with enough supply. Every citing paper is assigned to half A or half B from the published seed, so the two test sets share no papers. In each half and category we drew 360 packages at random: 330 are annotated now and 30 wait as reserve. Batches mix all six categories, nine or ten of each, and never hold two packages from the same citing paper. Batch names (L001 to L072) and package ids are shuffled across both sets, so neither reveals which set a batch belongs to. Basis, Improvement/Modification and Further Reading come in round 2.

## Slide 9: How the batches reach your folder
RELEASE PLAN · GOING FORWARD
Wave 1
now
8 batches, 4 per set. Everyone gets 2: one from each set.
440 packages
Check
when wave 1 is complete
Correction rate per set and category decides the reserve (next slide).
decision
Wave 2
19-10-26
64 batches, 16 per person. Does not wait for the check.
3,520 packages
Wave R
after the check, if any
Released reserve only, in extra batches shared evenly.
0–720 packages
Round 2
after the pool extension
Basis, Improvement/Modification, Further Reading.
[quota]
calib2 and A3 round 1 · 9 · Sheets appear in anotadores/<your id>/; no email per Sheet, we post when a wave is out
Notes: Wave 1 is small on purpose: about 10% of each set, so we can measure the correction rate early. Everyone has one batch of each set in it. When wave 1 is complete, the check decides whether any reserve is needed; wave 2 is independent of that decision and carries the other 64 batches, 16 per person. If reserve is released, it comes as a separate wave R of extra batches, spread so nobody gets more than one batch beyond the others. Round 2 follows the same process for the three remaining categories once the pool has been extended and the quotas agreed with the director. Fill in the wave 2 date and the round-2 quota before sharing.

## Slide 10: Over 10% corrected: 30 more packages
RESERVE · WHEN IT IS RELEASED
The rule
After wave 1, for each set and category: corrected answers ÷ all answers, both annotators counted. Above 10%, its 30 reserve packages are annotated too.
Why count answers
A package leaves its category only if the final label changes. A correction by one person goes to adjudication and often stays; counting answers weighs both annotators.
Example
About 37 packages per set and category in wave 1, so 74 answers.
Corrected | Rate | Reserve
7 of 74 | 9.5% | not released
8 of 74 | 10.8% | released
Each release adds 30 packages, 60 annotations. Once written, the decision is frozen.
calib2 and A3 round 1 · 10 · contract §6 · the check also shows packages with any and with both annotators correcting
Notes: The reserve exists so that each set keeps at least 300 instances per category after adjudication, because a package whose final label differs from its pre-label moves to another category. After wave 1 we compute, for each of the 12 set-and-category cells, the share of answers that changed the pre-label. Above 10%, that cell’s 30 reserve packages go into extra batches. We count answers rather than packages: if one annotator corrects and the other confirms, the package goes to adjudication and often keeps its category. The check also lists packages where either annotator corrected and where both did, so the team can see the decision before it is frozen.

## Slide 11: Working through a batch
YOUR BATCHES · SAME SHEET AS CALIB2
Where: anotadores/<your id>/, one Sheet per batch, named <id>_L0xx. The name does not say which test set it belongs to.
Order: one batch at a time; finish wave 1 first.
Colours: yellow pending · amber corrected · pink to fix (unclear without a note, repeated secondary).
Resumen tab: total minutes and any comments on the batch.
The columns
Cols | What
A–C | Package, target sentence, citing paragraph
D | Pre-label from the judges
E–I | Yours: main label, secondaries, confidence, notes
J–L | Co-cited count, cited title, abstract
M–O | Top-3 chunks, folded: open with +
calib2 and A3 round 1 · 11 · only E–I are editable · secondaries only in extreme cases (guide rev3.1)
Notes: Nothing changes from calib2 except the size: 55 packages per batch instead of 27, and two batches per person in wave 1. The batch name is neutral on purpose, so nobody knows whether a batch is their own group’s test set or the other group’s. The main label is required on every row; confidence too. A note is required for unclear and recommended when you correct, naming the rule. Open the chunks only when the title and abstract are not enough, as in the guide. Log total minutes on the Resumen tab when you finish the batch.

## Slide 12: Each group gives up about 10% of citing papers
TRAINING DATA · WHAT THE TEST SETS COST
≈10%
of citing papers out of each group’s training: 2,038 (G14) and 2,022 (G15) of 19,741
2,833
lowest train + test count of the five covered categories, either group; target 2,000
0
unarXive text in any shared file: identifiers only; text stays in the private Sheets
Each group trains on every paper except its own test set’s citing papers, including the other group’s test set with gold labels. Originator, Basis, Improvement/Modification and Further Reading stay short because of supply, not because of the test sets.
calib2 and A3 round 1 · 12 · sampler preview (8.1), 18 Oct · worst case, unused reserve still excluded · contract §10
Notes: The director’s conditions: the full corpus may be used for training and testing as long as it is released as identifiers plus a reconstruction script, and each group meets its validation quota with its own samples. The exclusion list removes, for each group, every pool row whose citing paper is in its own test set. That is about 2,030 papers per group, roughly 10% of the 19,741 in the pool. Most of the rows lost are the test packages themselves; the extra cost is roughly 50 to 220 rows per covered category. Application is the lowest of the five covered categories at 2,833 for group 14. Originator ends near 1,300 per group and Basis, Improvement/Modification and Further Reading near 500, which is a supply problem for round 2, not an effect of the exclusion.

## Slide 13: What happens next, and what we still need
NEXT STEPS · OPEN DECISIONS
Next steps
Wave 1 complete by [19-10-26]: 2 batches each
Check: reserve decision, shown to the team before it is frozen
Wave 2 out [19-10-26]: 16 batches each
Close round 1: κ and α report, adjudication, gold test sets
Open decisions
Metrics lead: one person computes every metric
Adjudicating pair: one per group, not the sampling lead
Dates!!!
Round-2 quotas: Basis, Improvement/Modification, Further Reading
calib2 and A3 round 1 · 13 · contract §9, §11, §12
Notes: The near-term steps are all about round 1: finish wave 1, run the reserve check, release wave 2, then close the round with the agreement report and adjudication. The open decisions are the ones still marked as pending in the contract. The metrics lead computes every agreement figure with one shared script so both groups report the same numbers. The adjudicating pair needs one person from each group, and not the sampling lead, who has access to every Sheet. Dates and the round-2 quotas need the director.